## Sheet1
Related User Story | Task Description | Assigned To | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
Fix Delete Functions | Fix delete when user is a group manager
(Give informative feedback) | Fix delete when group manager is a project lead | Eman | 2 | 2 | 0
| Fix approval rejection process | Jabesi
Board | Create Board UI | Jacob | 4 | 0 | 0
| Create Edit Board UI (CRUD) | Jacob | 4 | 0 | 0
| Add column | Jacob | 5 | 3 | 0
| Delete Column | Jacob | 3 | 3 | 0
| Rename Column | Jacob | 3 | 3 | 0
| Reorder Column | Jacob | 5 | 5 | 0
Assignments | Assign stage of board to a group | Jacob | 8 | 6 | 0
Permissions | Implement board permissions | Jacob | 0.5 | 0.5 | 0
Revise after first sprint meeting
| Estimate Totals |  | 34.5 | 22.5 | 0 | 0 | 0