## Sheet1
Related User Story | Task Description | Assigned To | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
Logout | Create Logout Page UI (maybe a modal) | Eman | 2 | 1 | 2
| Implement functionality for Logout | Eman | 2 | 0 | 2
System Wide | Add required field indication for CRUD operations | All
| Group priviledges | Jacob | 2 | 0 | 0
| Project priviledges | Jacob | 2 | 0 | 0
User Management Page | Fix roles (should be user or admin) | Jacob | 1 | 0 | 0
| Add Email/phone fields in create/edit | Jacob | 0.5 | 0 | 0
Group Management Page | Add Group | Eman | 2 | 2 | 2
| Edit Group | Eman | 2 | 2 | 2.5
| Remove Group | Eman | 2 | 0 | 3
| Update Group Page UI to be more user friendly | Eman | 3 | 0 | 3
Projects Page | Fix Add Project | Jabesi, Jacob | 10 | 4 | 7
| Fix Edit Project | Jabesi | 10 | 5 | 6
| Fix Remove Project | Jabesi | 5 | 5 | 0
| Update Project Page UI to be more user friendly | Jabesi | 5 | 4 | 0
| Add Group Aproval Process | Jabesi | 3 | 0 | 3
| Add Project List Filtering | Jabesi | 4 | 0 | 4.5
Paging | Paging on User Management
Paging on Group Management
Paging on Project Management
Testing & Documentation | Test User Management | Jacob | 8
| Test Group Management | Eman | 6
Test remaining classes
| Fix Class diagram | Jabesi | 6 | 0 |  | 6
| Update Wireframe | Jabesi | 2 | 0 |  | 1
| Test Project Management | Jabesi | 9 | 0 |  | 11
Revise after first sprint meeting
| Estimate Totals |  | 86.5 | 23 | 35 | 18 | 0