## Sheet1
Related User Story | Task Description | Assigned To | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
Logout | Create Logout Page UI (maybe a modal) | Eman
| Implement functionality for Logout | Eman
System Wide | Add required field indication for CRUD operations
Group priviledges
Project priviledges
User Management Page | Fix roles (should be user or admin) | Jacob
| Add Email/phone fields in create/edit | Jacob
Group Management Page | Add Group
Edit Group
Remove Group
Update Group Page UI to be more user friendly
Projects Page | Fix Add Project
Fix Edit Project
Fix Remove Project
| Update Project Page UI to be more user friendly | Jabesi
Paging | Paging on User Management
Paging on Group Management
Paging on Project Management
Revise after first sprint meeting
| Estimate Totals |  | 0 | 0 | 0 | 0 | 0