## Sheet1
Related User Story | Task Description | Assigned To | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
Fixes | Assign multiple groups to stage | Jacob | 5 | 0
| View board (not edit) | Eman | 3 | 4
| Fix Board Screen Size | Eman | 1 | 4
| Update delete User error message | Jabesi | 3
| Remove Manager restrictions on Board | Jabesi | 3
Tickets | Create Ticket | Jacob | 4 | 4 | 0
| Update Ticket Stage | Jabesi
| Assign Ticket to User | Jacob | 4 | 4 | 0
| View Ticket Details | Eman | 4 | 6
Revise after first sprint meeting
| Estimate Totals |  | 27 | 22 | 0 | 0 | 0