## Sheet1
Related User Story | Task Description | Assigned To | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
Login/Logout | Create Login Page UI | Emmanuel Olutoyin | 2
(Authentication) | Implement functionality for Login Page (and authentication) | Emmanuel Olutoyin | 2
| Create account/user page UI (acct. info) | Emmanuel Olutoyin | 2
| Implement functionality forcreate account/user Page | Emmanuel Olutoyin | 2
Landing Page | Create Landing Page and Nav Bar UI | Jabesi Abwe | 5 | 3 | 0
| Implement functionality for Landing Page and Nav Bar | Jabesi Abwe | 0
User Management Page | Create User Management Page UI | Jacob Evans | 2
| Implement functionality for User Management Page | Jacob Evans | 2
Group Management Page | Create Group Management Page UI | Jacob Evans | 2
| Implement functionality for Group Management Page | Jacob Evans | 2
Projects Page | Create Project Management Page UI (New Project, Edit Project, Assigne Group(s), Assigne Group Lead...) | Jabesi Abwe | 4 | 0 | 4
| Implement functionality for Project Management Page (who's on project, who's lead on project) | Jabesi Abwe | 10 | 0 | 13
Implement Tasks Management page Page (this goes along with the board creation)
Implement functionality for Tasks management Page (same with this)
Database | Design and implement a structured relational database (efficiently stores user data, group associations, project details, task management, and messaging records) | Jabesi, Jacob, Emmanuel | 4
| Implement entity relationships with appropriate primary and foreign keys | Jacob Evans | 2
Revise after first sprint meeting
| Estimate Totals |  | 41 | 3 | 17 | 0 | 0